## Summary
Bucket | Count | Notes
Total objects in registry | 126
Setup objects (setup=TRUE) | 92 | Fixed schema → migrate to Django ORM
Standard business objects (setup=FALSE, type=standard) | 23 | Dynamic schema → keep raw SQL via gateway
Custom business objects (setup=FALSE, type=custom) | 11 | User-defined → keep raw SQL via gateway
Already in Django ORM (db_table mapped) | 10 | 12 setup tables — audit & harden
Setup tables that are Django framework / Celery | 10 | Skip — managed by Django/Celery
Setup tables suspected legacy duplicates of business objects | 4 | customers/products/invoices/invoice_items
Setup tables remaining to migrate to Django ORM | 68 | Primary migration scope
REGISTRY GAPS (from AST scan + .sql review)
Missing setup table | 21
Missing business object | 5
Naming inconsistency | 4
Bug — likely typo | 2
Legacy duplicate | 4
Django-modeled, not in registry | 1
Total registry gaps | 40 | See Registry_Gaps sheet

## All_Objects
Category | Subcategory | Name | Label | Plural Label | Type | Setup? | Default Access Level | Deployment Status | Show Tab | Allow Reports | Allow Sharing | Track Field History | Prefix | Currently in Django ORM? | Django Model Source | Migration Recommendation
SETUP | Integration | apex_class | Apex Class | Apex Classes | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | app | App | Apps | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | app_permissions | App Permissions | App Permissionses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | approval_processes | Approval Processes | Approval Processeses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Audit / History | audit_trail_track | Audit Trail Track | Audit Trail Tracks | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Audit / History | audit_trails | Audit Trails | Audit Trailses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization (Django) | auth_group | Auth Group | Auth Groups | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization (Django) | auth_group_permissions | Auth Group Permissions | Auth Group Permissionses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization (Django) | auth_permission | Auth Permission | Auth Permissions | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration / Telephony | call_logs | Call Logs | Call Logses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Messaging | channel | Channel | Channels | standard | True |  |  | False | False | False | False |  | Yes | whatsapp/models.py | Already in Django ORM — audit & harden
SETUP | Platform Metadata | columns_metadata | Columns Metadata | Columns Metadatas | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | component | Component | Components | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration | connected_app | Connected App | Connected Apps | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Platform Metadata | custom_metadata | Custom Metadata | Custom Metadatas | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Platform Metadata | custom_setting | Custom Setting | Custom Settings | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Legacy / Possible duplicate of 'customer' | customers | Customers | Customerses | standard | True |  |  | False | False | False | False |  | No |  | Investigate — likely legacy duplicate of business object
SETUP | Reporting | dashboard | Dashboard | Dashboards | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Django Framework | django_admin_log | Django Admin Log | Django Admin Logs | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework (Celery Beat) | django_celery_beat_clockedschedule | Django Celery Beat Clockedschedule | Django Celery Beat Clockedschedules | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework (Celery Beat) | django_celery_beat_crontabschedule | Django Celery Beat Crontabschedule | Django Celery Beat Crontabschedules | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework (Celery Beat) | django_celery_beat_intervalschedule | Django Celery Beat Intervalschedule | Django Celery Beat Intervalschedules | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework (Celery Beat) | django_celery_beat_periodictask | Django Celery Beat Periodictask | Django Celery Beat Periodictasks | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework (Celery Beat) | django_celery_beat_periodictasks | Django Celery Beat Periodictasks | Django Celery Beat Periodictaskses | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework (Celery Beat) | django_celery_beat_solarschedule | Django Celery Beat Solarschedule | Django Celery Beat Solarschedules | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework | django_content_type | Django Content Type | Django Content Types | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework | django_migrations | Django Migrations | Django Migrationses | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Django Framework | django_session | Django Session | Django Sessions | standard | True |  |  | False | False | False | False |  | No |  | Skip — managed by Django/Celery framework
SETUP | Workflow | duplicate_rule | Duplicate Rule | Duplicate Rules | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | email_templates | Email Templates | Email Templateses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration | facebook_lead | Facebook Lead | Facebook Leads | standard | True |  |  | False | False | False | False |  | Yes | facebook/models.py | Already in Django ORM — audit & harden
SETUP | Audit / History | field_history_log | Field History Log | Field History Logs | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | field_permissions | Field Permissions | Field Permissionses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Audit / History | field_tracking_config | Field Tracking Config | Field Tracking Configs | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Platform Metadata | fields | Fields | Fieldses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Files | file | File | Files | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | flows | Flows | Flowses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Audit / History | group_assignment_tracker | Group Assignment Tracker | Group Assignment Trackers | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Audit / History (typo: 'history') | hsitory | Hsitory | Hsitories | standard | True |  |  | False | False | False | False |  | No |  | Rename to 'history' then migrate to Django ORM
SETUP | Files | import_wizard | Import Wizard | Import Wizards | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Legacy / Possible duplicate of 'invoice_item' | invoice_items | Invoice Items | Invoice Itemses | standard | True |  |  | False | False | False | False |  | No |  | Investigate — likely legacy duplicate of business object
SETUP | Legacy / Possible duplicate of 'invoice' | invoices | Invoices | Invoiceses | standard | True |  |  | False | False | False | False |  | No |  | Investigate — likely legacy duplicate of business object
SETUP | Integration / Telephony | landing_numbers | Landing Numbers | Landing Numberses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | layout_assignment | Layout Assignment | Layout Assignments | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | lead_capture | Lead Capture | Lead Captures | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | lightning_pages | Lightning Pages | Lightning Pageses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | listviews | Listviews | Listviewses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | matching_rule | Matching Rule | Matching Rules | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Messaging | message | Message | Messages | standard | True |  |  | False | False | False | False |  | Yes | whatsapp/models.py | Already in Django ORM — audit & harden
SETUP | Integration | named_credential | Named Credential | Named Credentials | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | node | Node | Nodes | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Platform Metadata | object | Object | Objects | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | object_permissions | Object Permissions | Object Permissionses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | owd | Owd | Owds | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration | package | Package | Packages | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | page_builder_assignment | Page Builder Assignment |  | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | page_layouts | Page Layouts | Page Layoutses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | path_builder | Path Builder | Path Builders | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | permission_sets | Permission Sets | Permission Setses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | process_builders | Process Builders | Process Builderses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Legacy / Possible duplicate of 'product' | products | Products | Productses | standard | True |  |  | False | False | False | False |  | No |  | Investigate — likely legacy duplicate of business object
SETUP | Authorization | profile | Profile | Profiles | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Sales Ops | regions | Regions | Regionses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration | remote_site_setting | Remote Site Setting | Remote Site Settings | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Reporting | reports | Reports | Reportses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | roles | Roles | Roleses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Sales Ops | sales | Sales | Saleses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration | salesforce_metadata | Salesforce Metadata | Salesforce Metadatas | standard | True |  |  | False | False | False | False |  | Yes | sf_integration/models.py | Already in Django ORM — audit & harden
SETUP | Integration | salesforce_settings | Salesforce Settings | Salesforce Settingses | standard | True |  |  | False | False | False | False |  | Yes | sf_integration/models.py | Already in Django ORM — audit & harden
SETUP | Integration | salesforce_sync | Salesforce Sync | Salesforce Syncs | standard | True |  |  | False | False | False | False |  | Yes | sf_integration/models.py | Already in Django ORM — audit & harden
SETUP | UI / Layout | search_layouts | Search Layouts | Search Layoutses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Audit / History | session_log | Session Log | Session Logs | standard | True |  |  | False | False | False | False |  | Yes | api/models.py:SessionLog | Already in Django ORM — audit & harden
SETUP | Platform Metadata | setup | Setup | Setups | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration | sf_integration_lead | Sf Integration Lead | Sf Integration Leads | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | sharing_records | Sharing Records | Sharing Recordses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | sharing_rules | Sharing Rules | Sharing Ruleses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | tab_permissions | Tab Permissions | Tab Permissionses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Platform Metadata | tables_metadata | Tables Metadata | Tables Metadatas | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | tabs | Tabs | Tabses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Sales Ops | task | Task | Tasks | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration / Telephony | telephony_config | Telephony Config | Telephony Configs | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | UI / Layout | theme | Theme | Themes | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | user_group | User Group | User Groups | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Authorization | user_group_users | User Group Users | User Group Userses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Audit / History | user_login_history | User Login History | User Login Histories | standard | True |  |  | False | False | False | False |  | Yes | api/models.py:UserLoginHistory | Already in Django ORM — audit & harden
SETUP | Identity | users | Users | Userses | standard | True |  |  | False | False | False | False |  | Yes | api/models.py:User | Already in Django ORM — audit & harden
SETUP | Authorization | users_user_permissions | Users User Permissions | Users User Permissionses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Integration | webhook | Webhook | Webhooks | standard | True |  |  | False | False | False | False |  | Yes | whatsapp/models.py | Already in Django ORM — audit & harden
SETUP | Workflow | workflow | Workflow | Workflows | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | workflow_edge | Workflow Edge | Workflow Edges | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | workflow_node | Workflow Node | Workflow Nodes | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
SETUP | Workflow | workflow_rules | Workflow Rules | Workflow Ruleses | standard | True |  |  | False | False | False | False |  | No |  | Migrate to Django ORM
BUSINESS / STANDARD | Standard business object | accounts | Account | Accounts | standard | False | Private | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | calendar | Calendar | Calendars | standard | False |  | deployed | True | True | True | False | CaX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | campaign | Campaign | Campaigns | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | campaign_member | Campaign Member | Campaign Members | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | case | Case | Cases | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | contact | Contact | Contacts | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | dashboard_folder | Dashboard Folder | Dashboard Folders | standard | False |  | deployed | True | True | True | False | DaF | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | event | Event | Events | standard | False |  | deployed | True | True | True | False | EvX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | incentive_slab | Incentive Slab | Incentive Slabs | standard | False |  | deployed | True | True | True | False | InS | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | invoice | Invoice | Invoices | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | invoice_item | Invoice Item | Invoice Items | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | leads | Lead | Leads | standard | False | Private | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | opportunity | Opportunity | Opportunities | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | opportunity_lineitem | Opportunity Line Item | Opportunity Line Items | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | period | Period | Periods | standard | False |  | deployed | True | True | True | False | PeX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | product | Product | Products | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | product_category | Product Category | Product Categories | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | quote | Quote | Quotes | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | quote_line_item | Quote Line Item | Quote Line Items | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | target | Target | Targets | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | target_item | Target Item | Target Items | standard | False |  | deployed | True | True | True | False | TaI | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | target_logic | Target Logic | Target Logics | standard | False |  | Deployed | True | True | False | True |  | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / STANDARD | Standard business object | target_plan | Target Plan | Target Plans | standard | False |  | deployed | True | True | True | False | TaP | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | an_object_for_testing | AN object for Testing | AN object for Testings | custom | False |  | deployed | True | True | True | True | AnOft | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | business | Business | Businesss | custom | False |  | In Development | False | False | False | False | BuX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | call | Call | Calls | custom | False |  | deployed | True | True | True | True | CaX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | collection | Collection | Collections | custom | False |  | In Development | False | False | False | False | CoX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | customer | Customer | Customers | custom | False |  | In Development | True | False | False | False | CuX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | issue | Issue | Issues | custom | False |  | deployed | True | True | True | True | IsX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | leave | Leave | Leaves | custom | False |  | In Development | False | False | False | False | LeX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | location_track | Location Track | Location Tracks | custom | False |  | In Development | False | False | False | False | LoT | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | test | Test | Tests | custom | False |  | deployed | True | True | True | False | TeX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | ticket | Ticket | Tickets | custom | False |  | In Development | True | True | True | True | TiX | No |  | Keep raw SQL — dynamic schema via metadata gateway
BUSINESS / CUSTOM | User-defined | visit | Visit | Visits | custom | False |  | In Development | False | False | False | False | ViX | No |  | Keep raw SQL — dynamic schema via metadata gateway

## Migration_Plan
Phase | Wave | Object Name | Label | Subcategory | Action | Notes
Phase 1 — Audit existing Django models | — | channel | Channel | Messaging | Audit & harden | whatsapp/models.py
Phase 1 — Audit existing Django models | — | facebook_lead | Facebook Lead | Integration | Audit & harden | facebook/models.py
Phase 1 — Audit existing Django models | — | message | Message | Messaging | Audit & harden | whatsapp/models.py
Phase 1 — Audit existing Django models | — | salesforce_metadata | Salesforce Metadata | Integration | Audit & harden | sf_integration/models.py
Phase 1 — Audit existing Django models | — | salesforce_settings | Salesforce Settings | Integration | Audit & harden | sf_integration/models.py
Phase 1 — Audit existing Django models | — | salesforce_sync | Salesforce Sync | Integration | Audit & harden | sf_integration/models.py
Phase 1 — Audit existing Django models | — | session_log | Session Log | Audit / History | Audit & harden | api/models.py:SessionLog
Phase 1 — Audit existing Django models | — | user_login_history | User Login History | Audit / History | Audit & harden | api/models.py:UserLoginHistory
Phase 1 — Audit existing Django models | — | users | Users | Identity | Audit & harden | api/models.py:User
Phase 1 — Audit existing Django models | — | webhook | Webhook | Integration | Audit & harden | whatsapp/models.py
Phase 2 — Migrate setup tables to Django ORM | Wave 1 — Core platform metadata | object | Object | Platform Metadata | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 1 — Core platform metadata | fields | Fields | Platform Metadata | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 1 — Core platform metadata | tables_metadata | Tables Metadata | Platform Metadata | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 1 — Core platform metadata | columns_metadata | Columns Metadata | Platform Metadata | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 1 — Core platform metadata | setup | Setup | Platform Metadata | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | profile | Profile | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | permission_sets | Permission Sets | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | roles | Roles | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | user_group | User Group | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | user_group_users | User Group Users | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | users_user_permissions | Users User Permissions | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | object_permissions | Object Permissions | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | field_permissions | Field Permissions | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | tab_permissions | Tab Permissions | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | app_permissions | App Permissions | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | sharing_records | Sharing Records | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | sharing_rules | Sharing Rules | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 2 — Authorization (high-risk) | owd | Owd | Authorization | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | app | App | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | tabs | Tabs | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | page_layouts | Page Layouts | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | page_builder_assignment | Page Builder Assignment | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | layout_assignment | Layout Assignment | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | lightning_pages | Lightning Pages | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | path_builder | Path Builder | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | search_layouts | Search Layouts | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | listviews | Listviews | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | theme | Theme | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 3 — UI / layout / navigation | component | Component | UI / Layout | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 4 — Reporting / files | reports | Reports | Reporting | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 4 — Reporting / files | dashboard | Dashboard | Reporting | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 4 — Reporting / files | file | File | Files | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 4 — Reporting / files | import_wizard | Import Wizard | Files | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | workflow | Workflow | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | workflow_node | Workflow Node | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | workflow_edge | Workflow Edge | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | workflow_rules | Workflow Rules | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | process_builders | Process Builders | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | flows | Flows | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | approval_processes | Approval Processes | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | node | Node | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | matching_rule | Matching Rule | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | duplicate_rule | Duplicate Rule | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | lead_capture | Lead Capture | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 5 — Workflow / automation | email_templates | Email Templates | Workflow | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | apex_class | Apex Class | Integration | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | connected_app | Connected App | Integration | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | named_credential | Named Credential | Integration | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | remote_site_setting | Remote Site Setting | Integration | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | package | Package | Integration | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | sf_integration_lead | Sf Integration Lead | Integration | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | landing_numbers | Landing Numbers | Integration / Telephony | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | telephony_config | Telephony Config | Integration / Telephony | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 6 — Integration / telephony | call_logs | Call Logs | Integration / Telephony | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 7 — Audit / history | audit_trails | Audit Trails | Audit / History | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 7 — Audit / history | audit_trail_track | Audit Trail Track | Audit / History | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 7 — Audit / history | field_history_log | Field History Log | Audit / History | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 7 — Audit / history | field_tracking_config | Field Tracking Config | Audit / History | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 7 — Audit / history | hsitory | Hsitory | Audit / History (typo: 'history') | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 7 — Audit / history | group_assignment_tracker | Group Assignment Tracker | Audit / History | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 8 — Misc / sales ops | regions | Regions | Sales Ops | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 8 — Misc / sales ops | sales | Sales | Sales Ops | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 8 — Misc / sales ops | task | Task | Sales Ops | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 8 — Misc / sales ops | custom_metadata | Custom Metadata | Platform Metadata | Build Django model + migration; replace raw SQL callsites
Phase 2 — Migrate setup tables to Django ORM | Wave 8 — Misc / sales ops | custom_setting | Custom Setting | Platform Metadata | Build Django model + migration; replace raw SQL callsites
Phase 3 — Resolve legacy duplicates | — | customers | Customers | Legacy / Possible duplicate of 'customer' | Investigate & merge or delete | Possible duplicate of business object 'customer'
Phase 3 — Resolve legacy duplicates | — | products | Products | Legacy / Possible duplicate of 'product' | Investigate & merge or delete | Possible duplicate of business object 'product'
Phase 3 — Resolve legacy duplicates | — | invoices | Invoices | Legacy / Possible duplicate of 'invoice' | Investigate & merge or delete | Possible duplicate of business object 'invoice'
Phase 3 — Resolve legacy duplicates | — | invoice_items | Invoice Items | Legacy / Possible duplicate of 'invoice_item' | Investigate & merge or delete | Possible duplicate of business object 'invoice_item'
Phase 4 — Skip (Django/Celery managed) | — | django_admin_log | Django Admin Log | Django Framework | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_celery_beat_clockedschedule | Django Celery Beat Clockedschedule | Django Framework (Celery Beat) | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_celery_beat_crontabschedule | Django Celery Beat Crontabschedule | Django Framework (Celery Beat) | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_celery_beat_intervalschedule | Django Celery Beat Intervalschedule | Django Framework (Celery Beat) | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_celery_beat_periodictask | Django Celery Beat Periodictask | Django Framework (Celery Beat) | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_celery_beat_periodictasks | Django Celery Beat Periodictasks | Django Framework (Celery Beat) | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_celery_beat_solarschedule | Django Celery Beat Solarschedule | Django Framework (Celery Beat) | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_content_type | Django Content Type | Django Framework | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_migrations | Django Migrations | Django Framework | No action — framework owns it
Phase 4 — Skip (Django/Celery managed) | — | django_session | Django Session | Django Framework | No action — framework owns it
Phase 5 — Business objects (raw SQL via gateway) | Standard | accounts | Account | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | an_object_for_testing | AN object for Testing | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | business | Business | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | calendar | Calendar | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | call | Call | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | campaign | Campaign | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | campaign_member | Campaign Member | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | case | Case | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | collection | Collection | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | contact | Contact | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | customer | Customer | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | dashboard_folder | Dashboard Folder | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | event | Event | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | incentive_slab | Incentive Slab | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | invoice | Invoice | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | invoice_item | Invoice Item | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | issue | Issue | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | leads | Lead | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | leave | Leave | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | location_track | Location Track | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | opportunity | Opportunity | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | opportunity_lineitem | Opportunity Line Item | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | period | Period | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | product | Product | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | product_category | Product Category | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | quote | Quote | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | quote_line_item | Quote Line Item | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | target | Target | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | target_item | Target Item | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | target_logic | Target Logic | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Standard | target_plan | Target Plan | Standard business object | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | test | Test | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | ticket | Ticket | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model
Phase 5 — Business objects (raw SQL via gateway) | Custom | visit | Visit | User-defined | Route through hardened ORM gateway (sql.Identifier + schema authority) | Dynamic schema — cannot be a static Django model

## Registry_Gaps
Kind | Table / Item | Label / Note | Evidence (file:line) | Recommended Action
Missing setup table | callactivity | Call Activity | default_tables.sql:933 | Add registry row (setup=TRUE); telephony call-activity log
Missing setup table | dashboard_assignment | Dashboard Assignment | default_tables.sql (dashboard module) | Add registry row (setup=TRUE); dashboard share assignment
Missing setup table | dashboard_folder_sharing | Dashboard Folder Sharing | default_tables.sql:739 | Add registry row (setup=TRUE)
Missing setup table | email_provider_setup | Email Provider Setup | default_tables.sql:785 | Add registry row (setup=TRUE); OAuth-token storage (encrypted since Phase 0.8)
Missing setup table | field_mapping | Field Mapping | default_tables.sql:146 | Add registry row (setup=TRUE)
Missing setup table | homepage_assignment | Homepage Assignment | api/ORM/setup/newprofile.py:88,93 | Add registry row (setup=TRUE); will be migrated to Django ORM
Missing setup table | notifications | Notifications | default_tables.sql:905 | Add registry row (setup=TRUE); registry currently has BL route name 'notification' but no entry for the actual table
Missing setup table | org_company | Organization Company | default_tables.sql (legacy column-mapping table) | Add registry row (setup=TRUE); investigate whether still used
Missing setup table | organizations | Organizations | adminuser/services/organizations.py:28,53; api/models.py:Organization | Add registry row (setup=TRUE); already has Django model
Missing setup table | otp_verification_sessions | OTP Verification Sessions | public/auth/otp_verification.py:156,198 | Add registry row (setup=TRUE); auth/OTP flow
Missing setup table | page_builder | Page Builder | api/ORM/setup/update_page_builder.py:28 | Add registry row (setup=TRUE); distinct from registered 'page_builder_assignment'
Missing setup table | page_component | Page Component | api/ORM/setup/update_page_builder.py:66,78 | Add registry row (setup=TRUE); page-builder child table
Missing setup table | report_folder_sharing | Report Folder Sharing | default_tables.sql:847 | Add registry row (setup=TRUE)
Missing setup table | shared_records | Shared Records (per-record sharing) | default_tables.sql:873 | Add registry row (setup=TRUE); DISTINCT from 'sharing_records' — sharing_records is per-object, shared_records is per-record
Missing setup table | telephony_user | Telephony User | default_tables.sql:923 | Add registry row (setup=TRUE); referenced in api/telephony/views.py
Missing setup table | tenant_provisioning_errors | Tenant Provisioning Errors | public/utils/error_log.py:20 | Add registry row (setup=TRUE); tenant onboarding error log
Missing setup table | user_gmail_tokens | User Gmail Tokens | default_tables.sql:705 | Add registry row (setup=TRUE); legacy — superseded by email_provider_setup but still created
Missing setup table | user_group_profiles | User Group Profiles | utils/usergroup_utils.py:305 | Add registry row (setup=TRUE); junction table for user_group <-> profile
Missing setup table | user_group_public_groups | User Group Public Groups | utils/usergroup_utils.py:317; api/workflows/workflow_executor.py:552 | Add registry row (setup=TRUE); junction for nested user groups
Missing setup table | user_outlook_tokens | User Outlook Tokens | default_tables.sql:720 | Add registry row (setup=TRUE); legacy — superseded by email_provider_setup but still created
Missing setup table | whatsapp_message | WhatsApp Message | api/BL/whatsapp/utils.py:18,67 | Add registry row (setup=TRUE); chat-message store
Missing business object | activity | Activity | tables.sql defines `CREATE TABLE activity` but it's not in the object registry as a business object | Register as business object (setup=FALSE)
Missing business object | dashboard_component | Dashboard Component | sqlfiles/mockdata/reports.sql | Add registry row; child of dashboard
Missing business object | dashboard_folders | Dashboard Folders | sqlfiles/mockdata/reports.sql | Plural form referenced; registry has 'dashboard_folder' singular - pick one and reconcile
Missing business object | email | Email (record) | tables.sql defines `CREATE TABLE email` for sent-email logging; not in the registry | Register as business object (setup=FALSE)
Missing business object | report_folder | Report Folder | sqlfiles/mockdata/reports.sql | Add registry row (setup=FALSE); related to 'reports' (already registered)
Naming inconsistency | dashboard_folder vs dashboard_folders | Dashboard Folder | registry: dashboard_folder (singular); code: dashboard_folders (plural) | Standardize on one form across registry, code, and mockdata
Naming inconsistency | report (default_tables.sql) vs reports (registry) | Report | default_tables.sql:320 has `CREATE TABLE report`; registry has 'reports' as the setup name | Pick one: either rename DDL to reports or update the registry to use 'report'
Naming inconsistency | reports vs report vs report_folder | Report | registry: 'reports'; code uses 'report' and 'report_folder' too | Standardize and register all related tables
Naming inconsistency | shared_records vs sharing_records | Two genuinely different tables, names too similar | default_tables.sql defines BOTH; sharing_records is per-object, shared_records is per-record | Rename one to disambiguate (suggest: per_record_shares) and update all references
Bug — likely typo | hsitory | Probably means 'history' | registry row in objects.sql | Rename to 'history' before migration
Bug — likely typo | organization (singular) | Probably means 'organizations' | api/pdfgen/views.py:74 | Fix the SQL string to use 'organizations'
Legacy duplicate | customers (setup) vs customer (business) | Customer | objects.sql registers both | Investigate which is actually used; merge or delete the unused one
Legacy duplicate | invoice_items (setup) vs invoice_item (business) | Invoice Item | objects.sql registers both | Investigate which is actually used; merge or delete the unused one
Legacy duplicate | invoices (setup) vs invoice (business) | Invoice | objects.sql registers both | Investigate which is actually used; merge or delete the unused one
Legacy duplicate | products (setup) vs product (business) | Product | objects.sql registers both | Investigate which is actually used; merge or delete the unused one
Django-modeled, not in registry | facebookleadwebhooks | Facebook Lead Webhooks | facebook/models.py (currently commented out) | Add registry row OR delete the Django model — currently dead code
Vestigial registry entry | apex_class, approval_processes, auth_group, columns_metadata, component, connected_app, custom_metadata, custom_setting, duplicate_rule, file, flows, group_assignment_tracker, import_wizard, lead_capture, lightning_pages, matching_rule, named_credential, node, package, permission_sets, process_builders, regions, remote_site_setting, sales, setup, sf_integration_lead, sharing_rules, tables_metadata, tabs, theme, users_user_permissions, workflow_rules | Aspirational Salesforce-clone features | Registered as setup=TRUE but no DDL in default_tables.sql, organisation.py, or app models; no SQL queries reference them | Bulk-investigate; delete vestigial rows after confirming none are queried at runtime
Vestigial registry entry | owd | Org-Wide Defaults table | Registered as setup=TRUE but no DDL anywhere; no FROM owd queries. Phase 2 default-deny work uses sharing_records exclusively. | Either build out OR delete the registry row + drop the Wave 2 OrganizationWideDefault model
Vestigial registry entry | roles | Aspirational Salesforce-style role hierarchy | Registered as setup=TRUE but no CREATE TABLE in tables.sql / default_tables.sql / organisation.py / app models; no FROM roles queries in the codebase | Either build out the role-hierarchy feature OR delete the registry row + drop the Wave 2 Role model

## DDL_Cross_Check
Table Name | In Registry | Registry Type | default_tables.sql | tables.sql | Inline organisation.py | App models.py | Phase 2 Wave 2 model | Verdict
accounts | Yes | standard |  | Yes |  |  |  | OK
activity | No | - |  | Yes |  |  |  | GAP — DDL exists, registry row missing
an_object_for_testing | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
apex_class | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
app | Yes | setup | Yes |  |  |  |  | OK
app_permissions | Yes | setup | Yes |  |  |  | Yes | OK
approval_processes | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
audit_trail_track | Yes | setup | Yes |  |  |  |  | OK
audit_trails | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
auth_group | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
auth_group_permissions | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
auth_permission | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
business | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
calendar | Yes | standard |  | Yes |  |  |  | OK
call | Yes | custom |  | Yes |  |  |  | OK
call_logs | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
callactivity | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
campaign | Yes | standard |  | Yes |  |  |  | OK
campaign_member | Yes | standard |  | Yes |  |  |  | OK
case | Yes | standard |  | Yes |  |  |  | OK
channel | Yes | setup |  |  |  | Yes |  | OK
collection | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
columns_metadata | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
component | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
connected_app | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
contact | Yes | standard |  | Yes |  |  |  | OK
custom_metadata | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
custom_setting | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
customer | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
customers | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
dashboard | Yes | setup | Yes |  |  |  |  | OK
dashboard_assignment | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
dashboard_component | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
dashboard_folder | Yes | standard | [5 empty] | VESTIGIAL — registered but no DDL anywhere
dashboard_folder_sharing | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
dashboard_folders | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
django_admin_log | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_celery_beat_clockedschedule | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_celery_beat_crontabschedule | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_celery_beat_intervalschedule | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_celery_beat_periodictask | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_celery_beat_periodictasks | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_celery_beat_solarschedule | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_content_type | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_migrations | Yes | setup | [5 empty] | OK — Django/Celery framework table
django_session | Yes | setup | [5 empty] | OK — Django/Celery framework table
duplicate_rule | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
email | No | - |  | Yes |  |  |  | GAP — DDL exists, registry row missing
email_provider_setup | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
email_templates | Yes | setup | Yes |  |  |  |  | OK
event | Yes | standard |  | Yes |  |  |  | OK
facebook_lead | Yes | setup |  |  |  | Yes |  | OK
facebookleadwebhooks | No | - |  |  |  | Yes |  | GAP — DDL exists, registry row missing
field_history_log | Yes | setup | Yes |  |  |  |  | OK
field_mapping | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
field_permissions | Yes | setup | Yes |  |  |  | Yes | OK
field_tracking_config | Yes | setup | Yes |  |  |  |  | OK
fields | Yes | setup | Yes |  |  |  | Yes | OK
file | Yes | setup |  | Yes |  |  |  | OK
flows | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
group_assignment_tracker | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
homepage_assignment | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
hsitory | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
import_wizard | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
incentive_slab | Yes | standard |  | Yes |  |  |  | OK
invoice | Yes | standard |  | Yes |  |  |  | OK
invoice_item | Yes | standard |  | Yes |  |  |  | OK
invoice_items | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
invoices | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
issue | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
landing_numbers | Yes | setup | Yes |  |  |  |  | OK
layout_assignment | Yes | setup | Yes |  |  |  |  | OK
lead_capture | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
leads | Yes | standard |  | Yes |  |  |  | OK
leave | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
lightning_pages | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
listviews | Yes | setup | Yes |  |  |  |  | OK
location_track | Yes | custom |  | Yes |  |  |  | OK
matching_rule | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
message | Yes | setup |  |  |  | Yes |  | OK
named_credential | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
node | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
notifications | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
object | Yes | setup | Yes |  |  |  | Yes | OK
object_permissions | Yes | setup | Yes |  |  |  | Yes | OK
opportunity | Yes | standard |  | Yes |  |  |  | OK
opportunity_lineitem | Yes | standard |  | Yes |  |  |  | OK
org_company | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
organizations | No | - |  |  |  | Yes |  | GAP — DDL exists, registry row missing
owd | Yes | setup |  |  |  |  | Yes | VESTIGIAL — registered but no DDL anywhere
package | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
page_builder | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
page_builder_assignment | Yes | setup | Yes |  |  |  |  | OK
page_component | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
page_layouts | Yes | setup | Yes |  |  |  |  | OK
path_builder | Yes | setup | Yes |  |  |  |  | OK
period | Yes | standard |  | Yes |  |  |  | OK
permission_sets | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
process_builders | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
product | Yes | standard |  | Yes |  |  |  | OK
product_category | Yes | standard |  | Yes |  |  |  | OK
products | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
profile | Yes | setup |  |  | Yes |  | Yes | OK
quote | Yes | standard |  | Yes |  |  |  | OK
quote_line_item | Yes | standard |  | Yes |  |  |  | OK
regions | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
remote_site_setting | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
report | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
report_folder | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
report_folder_sharing | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
reports | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
roles | Yes | setup |  |  |  |  | Yes | VESTIGIAL — registered but no DDL anywhere
sales | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
salesforce_metadata | Yes | setup |  |  |  | Yes |  | OK
salesforce_settings | Yes | setup |  |  |  | Yes |  | OK
salesforce_sync | Yes | setup |  |  |  | Yes |  | OK
search_layouts | Yes | setup | Yes |  |  |  |  | OK
session_log | Yes | setup |  |  |  | Yes |  | OK
setup | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
sf_integration_lead | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
shared_records | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
sharing_records | Yes | setup | Yes |  |  |  | Yes | OK
sharing_rules | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
tab_permissions | Yes | setup | Yes |  |  |  | Yes | OK
tables_metadata | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
tabs | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
target | Yes | standard |  | Yes |  |  |  | OK
target_item | Yes | standard |  | Yes |  |  |  | OK
target_logic | Yes | standard |  | Yes |  |  |  | OK
target_plan | Yes | standard |  | Yes |  |  |  | OK
task | Yes | setup | Yes |  |  |  |  | OK
telephony_config | Yes | setup | Yes |  |  |  |  | OK
telephony_user | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
test | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
theme | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
ticket | Yes | custom | [5 empty] | VESTIGIAL — registered but no DDL anywhere
user_gmail_tokens | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
user_group | Yes | setup | Yes |  |  |  | Yes | OK
user_group_profiles | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
user_group_public_groups | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
user_group_users | Yes | setup | Yes |  |  |  | Yes | OK
user_login_history | Yes | setup |  |  |  | Yes |  | OK
user_outlook_tokens | No | - | Yes |  |  |  |  | GAP — DDL exists, registry row missing
users | Yes | setup |  |  | Yes | Yes |  | OK
users_user_permissions | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere
visit | Yes | custom |  | Yes |  |  |  | OK
webhook | Yes | setup |  |  |  | Yes |  | OK
workflow | Yes | setup | Yes |  |  |  |  | OK
workflow_edge | Yes | setup | Yes |  |  |  |  | OK
workflow_node | Yes | setup | Yes |  |  |  |  | OK
workflow_rules | Yes | setup | [5 empty] | VESTIGIAL — registered but no DDL anywhere